## Executive Summary
DappaAi — PoC & Phase 1 Sprint Plan
Created: 2026-03-22 ¦ Covers: Phase 0 (Weeks 1–8) + Phase 1 MVP (Weeks 9–24)
Phase Summary
Phase | Deliverables | Status | Notes
Phase 0 (PoCs) | 11 deliverables (PoC 1 + PoC 2) | COMPLETE | Scoring engine, LLM reasoning, evaluation framework built and validated
Phase 1 (MVP) | 21 feature requirements across 5 core areas | COMPLETE (code) | 20 complete, 1 deferred (AlayaCare app notifications → Phase 2)
Infrastructure Migration | 4 sprints / 8 weeks | NEXT | Migrate Supabase/Drizzle → Xano + Upstash, real SMS/email providers
Timeline Overview
Weeks | Sprint | Focus | Status
1–2 | S1–S2 | Scoring engine core | DONE
2–3 | S3 | Integration workflows + edge cases | DONE
3–4 | S4 | Scenario testing + PoC 1 deliverable | DONE
4–5 | S5 | LLM provider selection + prompt engineering | DONE
5–6 | S6 | Escalation evaluation framework | DONE
6–7 | S7 | Recommend API + PoC 2 deliverable | DONE
7 | S8 | Webhook event processing | DONE
8–9 | P1.1 | Workflow orchestrator + DB tables | DONE
9–10 | P1.3 | Communication layer (mock SMS/email) | DONE
10–11 | P1.4 | Cascade engine + escalation engine | DONE
11–12 | P1.5 | Operations dashboard + escalation console | DONE
12–13 | P1.7 | Audit trail + analytics + chat tools | DONE
13–14 | P1.8 | Learning system + E2E tests | DONE
15–16 | M1 | Xano foundation + CRUD template | NEXT
17–18 | M2 | Upstash Workflow + webhook pipeline | PLANNED
19–20 | M3 | SMS integration + human actions | PLANNED
21–22 | M4 | Dashboard migration + go-live prep | PLANNED
23 | — | UAT with Dovida staff | PLANNED
24 | — | Production launch | PLANNED

## PoC Deliverables
PoC 1 Deliverables (Sprints 1–4)
# | Description | Sprint | Status | Evidence
1.1 | Technical architecture document — AlayaCare integration approach | S1–S2 | DONE | docs/scoring-engine-architecture.md, docs/ARCHITECTURE.md
1.2 | Working prototype of scoring dimensions with validation results | S1–S2 | DONE | src/services/scoring/ — 11 files, 61 tests, 32 scenarios validated
1.3 | API capability matrix | S3 | DONE | docs/poc1-edge-cases.md, docs/poc1-workarounds.md
1.4 | Identified limitations with workarounds | S3 | DONE | docs/poc1-workarounds.md — 5 manual steps, 6 API gaps, 4 limitations
1.5 | Security and compliance requirements | S3 | DONE | docs/poc1-security-assessment.md — auth, traceability, compliance
1.6 | Estimated integration effort for Phase 1 | S4 | DONE | docs/poc1-production-pathway.md — deployment checklist + effort estimates
PoC 2 Deliverables (Sprints 5–7)
# | Description | Sprint | Status | Evidence
2.1 | Technical report with LLM performance metrics | S7 | DONE | docs/poc2-deliverable.md — formal technical report
2.2 | Recommended provider and approach | S5 | DONE | AWS Bedrock (Haiku 4.5), temperature 0.3, structured JSON output
2.3 | Escalation criteria tuning recommendations | S6–S7 | DONE | 7 escalation criteria in ROSTERING_SYSTEM_PROMPT, confusion matrix evaluation
2.4 | Example decision explanations | S7 | DONE | LLMRecommendation.primary.explanation + factors_considered[] + trade_offs[]
2.5 | Integration pathway for Phase 1 agent logic | S7 | DONE | Recommend endpoint + evaluation framework + UI panel
Integration Workflows (Sprints 3–4)
Req ID | Requirement | Status | Notes
R3.1 | Query workflow ("Find available caregivers...") | DONE | POST /api/v1/availability
R3.2 | Assignment workflow ("Assign caregiver to shift") | PARTIAL | Match → select → offer tested; no real SMS/email notification
R3.3 | Status monitoring ("Check shift status") | PARTIAL | VisitDetailCard + getShiftStatus() + webhook receiver; no real-time polling
R3.5 | Data completeness validation | DONE | computeMatch generates warnings
R3.6 | Edge case documentation | DONE | docs/poc1-edge-cases.md
R3.7 | Security/compliance/audit assessment | DONE | docs/poc1-security-assessment.md
R1.6 | Rate limit testing | NOT STARTED | Deferred — needs real AlayaCare sandbox
R3.4 | API response time testing | NOT STARTED | Deferred — needs real AlayaCare sandbox

## Phase 1 Features
Sprint 8: Webhook Event Processing
Feature | Status | Implementation
Webhook receiver with M2M auth | DONE | POST /api/v1/webhooks/alayacare, timing-safe secret comparison
Idempotent event processing | DONE | Two-layer: SELECT check + unique constraint catch
Event dispatcher + 7 handlers | DONE | Module-level handler registry, visit/employee/client events
workflow_events table | DONE | Migration 011, no RLS (system data)
Debouncer for scoring-heavy events | DONE | WebhookDebouncer with configurable WEBHOOK_DEBOUNCE_MS
Sprint P1.1–P1.2: Workflow Orchestrator + DB Tables
Feature | Status | Implementation
11-state machine | DONE | detected → gathering → scoring → reasoning → contacting → cascading → accepted → assigned → escalated → completed → cancelled
3 new DB tables | DONE | roster_tasks, roster_audit_log, roster_daily_metrics (migration 012)
Urgency classifier | DONE | planned vs urgent
Data validator | DONE | pre-flight checks before scoring
Sprint P1.3–P1.4: Communication + Cascade/Escalation
Feature | Deliverable Ref | Status | Implementation
SMS-based shift notifications | 3.1 | DONE | Mock SMS provider (Twilio stub)
Cascade logic (sequential + parallel) | 3.1 | DONE | cascade-engine.ts — sequential (planned, 2hr) + parallel (urgent, 20min)
Escalation decision logic | 4.3 | DONE | escalation-engine.ts — time, contact count, LLM-recommended triggers
Email-based communication | 3.2 | DONE | Mock email provider (SES stub)
Response pattern tracking | 3.1 | DONE | score-acceptance.ts with 30-day decay feedback loop
AlayaCare app notification | 3.3 | DEFERRED | Phase 2 — requires AlayaCare push notification API access
Sprint P1.5–P1.7: Human-in-the-Loop Interface
Feature | Deliverable Ref | Status | Implementation
Real-time operations dashboard | 5.1 | DONE | app/(app)/roster/page.tsx + task cards + activity feed
Escalation management console | 5.2 | DONE | app/(app)/escalations/page.tsx + escalation cards + candidate list
Audit trail and transparency | 5.3 | DONE | roster_audit_log table + audit timeline UI + searchable API
Basic analytics dashboard | 5.4 | DONE | app/(app)/analytics/page.tsx + daily metrics + analytics API
Conversational interface | 5.5 | DONE | 4 read + 3 write chat tools with SSE confirmation flow
Sprint P1.8: Learning System + Tests
Feature | Deliverable Ref | Status | Implementation
Outcome tracking | 4.4 | DONE | outcome-tracker.ts — structured learning data from resolved tasks
Pattern recognition | 4.4 | DONE | pattern-recognition.ts — always_declines, never_accepts, client_churn, high_escalation
Acceptance feedback loop | 3.1 | DONE | score-acceptance.ts — merges AlayaCare offers + DappaAi outcomes, 30-day decay
E2E tests | — | DONE | 10 E2E workflow + 5 performance benchmarks

## Completion Matrix
Phase 1 Core Features
# | Feature | Status | Notes
1.1–1.5 | LLM-powered caregiver matching engine | DONE | 5 dimensions, configurable weights, confidence, NL explanations
2.1–2.4 | AlayaCare integration layer | DONE | Bidirectional sync, webhooks, data quality, graceful degradation
3.1 | SMS-based shift notifications | DONE | Mock provider — needs Twilio cutover for production
3.2 | Email-based communication | DONE | Mock provider — needs SES/SendGrid cutover for production
3.3 | AlayaCare app integration | DEFERRED | Phase 2 — requires AlayaCare push notification API access
4.1–4.4 | Autonomous task-execution engine | DONE | State machine, cascade, escalation, learning
5.1–5.5 | Human-in-the-loop interface | DONE | Dashboard, escalation console, audit trail, analytics, chat

## Outstanding & BA Work
Requirements Not Yet Complete
Req ID | Description | Blocker | Effort | When
R1.6 | Rate limit testing | Needs real AlayaCare sandbox | 1 day | During Xano migration or sandbox access
R3.4 | API response time testing | Needs real AlayaCare sandbox | 1 day | During Xano migration or sandbox access
R3.2 | Real SMS/email notifications | Needs Twilio/SES accounts | 2 days | Sprint M3 (Xano migration)
R3.3 | Real-time status polling | Needs Upstash Workflow | 1 day | Sprint M2 (Xano migration)
P1.12 | AlayaCare app notification | Needs AlayaCare push API | Deferred | Phase 2
Business Analysis Work Completed
Analysis Area | Document | Status
Requirements definition | docs/poc.txt (source) | Received from stakeholders
Deliverables enumeration | docs/deliverables.txt | DONE
Requirements traceability | docs/poc-traceability.md | DONE
Scoring algorithm design | docs/scoring-engine-architecture.md, scoring-engine-whitepaper.md | DONE
Scoring plan reconciliation | docs/plans/scoring-engine-plan.md §1.2 | DONE
Data quality assessment | docs/poc1-edge-cases.md | DONE
API capability mapping | docs/poc1-workarounds.md | DONE
Security/compliance assessment | docs/poc1-security-assessment.md | DONE
Production integration pathway | docs/poc1-production-pathway.md | DONE
LLM evaluation methodology | docs/poc2-deliverable.md | DONE
Phase 1 rostering architecture | docs/phase1-rostering-architecture.md | DONE
Roster evolution strategy | docs/roster-evolution-strategy.md | DONE
Event architecture analysis | docs/ALAYACARE_EVENT_ARCHITECTURE_ANALYSIS.md | DONE
State machine design | docs/state-machine-architecture.md | DONE
Feature inventory | docs/features.md | DONE
Business Analysis Work Remaining
Analysis Area | Needed For | Effort | Priority
AlayaCare sandbox contract validation | Production cutover | 2–3 days | HIGH
Rate limit characterisation (AlayaCare API) | Production scaling | 1 day | MEDIUM
Multi-tenant requirements definition | Phase 2 | 2–3 days | LOW (post-MVP)
Email parsing rules for care manager handover emails | Deliverable 3.2 (inbound email) | 2 days | MEDIUM
Daily/weekly report content specification | Deliverable 3.2 (outbound email) | 1 day | MEDIUM
User acceptance testing scenarios for Dovida staff | Go-live validation | 2–3 days | HIGH

## Infrastructure Migration
Migration Sprint Summary (Xano + Upstash)
Sprint | Focus | Duration | Key Deliverables
M1 | Xano foundation + CRUD template | 2 weeks | All Xano tables, CRUD template for roster tasks, auth model, rate limiters
M2 | Upstash Workflow + webhook pipeline | 2 weeks | AlayaCare → QStash → Xano pipeline, durable workflow (score → reason → cascade)
M3 | SMS integration + human actions | 2 weeks | Twilio SMS send/receive, AlayaCare write-back, coordinator actions, chat tools migration
M4 | Dashboard migration + go-live prep | 2 weeks | All UI on Xano, old DB removed, production hardening P1 items, validation
External Dependencies
Dependency | Required By | Status
Xano account (paid plan) | Sprint M1 Day 1 | Needed
Upstash account (Redis + QStash) | Sprint M1 Day 7 | Needed
Twilio account + phone number | Sprint M3 (mock OK), M4 (real) | Needed for go-live
AlayaCare sandbox/production credentials | Sprint M4 | Needed for go-live
AWS Bedrock access (Haiku 4.5) | Sprint M2 | Already active
Production Hardening Items
Item | Priority | Effort | When
P1-01: Twilio signature verification | P1 | 2h | Sprint M4
P1-02: Dev reset endpoint guard | P1 | 30min | Sprint M4
P1-03: Bulk import + tenant_mapping | P1 | 8h | Sprint M4
P2-01: Per-tenant webhook endpoints | P2 | 4h | Before multi-tenant
P2-02: Xano RLS / tenant isolation | P2 | 4h | Before multi-tenant

## Success Criteria
PoC 1 Success Criteria
# | Criterion | Status | Evidence
1 | All critical read/write operations achievable via API | DONE | 6 GET + 2 POST + match + availability + recommend
2 | Match scores calculated for 30+ real shift scenarios | DONE | 32 scenarios, 32/32 expectations met
3 | Clear documentation of required manual workarounds | DONE | docs/poc1-workarounds.md
4 | Security and compliance requirements understood | DONE | docs/poc1-security-assessment.md
5 | Integration pathway to production is clear | DONE | docs/poc1-production-pathway.md
PoC 2 Success Criteria
# | Criterion | Target | Status
1 | LLM decisions match staff in straightforward scenarios | >=75% | DONE
2 | LLM correctly escalates ambiguous/edge cases | >=85% (FPR <20%) | DONE
3 | Reasoning explanations rated "clear and trustworthy" | >=80% | DONE
Phase 1 Success Metrics (post-launch validation)
Metric | Target | Measurement Method
Reduction in shift-filling phone calls | >=30% | Compare with pre-DappaAi baseline
Average time-to-fill (planned shifts) | <=20 minutes | resolved_at - detected_at on roster_tasks
First-contact acceptance rate | >=30% | contacts[0].response === 'accepted' / total tasks

## Documentation Inventory
Plans Directory (docs/plans/)
Document | Purpose | Status
poc-delivery-plan.md | End-to-end PoC + Phase 1 delivery plan | COMPLETE
scoring-engine-plan.md | Scoring engine implementation (Sprints 1–2) | COMPLETE
phase1-implementation-plan.md | Phase 1 autonomous shift filling (Sprints P1.1–P1.8) | COMPLETE
production-readiness-checklist.md | Go-live checklist for Phase 1 | ACTIVE — pending migration
xano-migration-sprint-plan.md | Xano + Upstash migration (Sprints M1–M4) | ACTIVE — next workstream
supabase-auth-migration.md | Cognito → Supabase auth migration | COMPLETE
cronicle-architecture-migration.md | Layered architecture migration | COMPLETE
restate-migration-plan.md | Evaluated alternative (Restate) | ARCHIVED
xstate-migration-plan.md | Evaluated alternative (XState + PostgreSQL) | ARCHIVED
Architecture & Primers (docs/, docs/primers/)
Document | Purpose
upstash-xano-architecture.md | Target architecture reference (Xano + Upstash)
upstash-xano-implementation-spec.md | Implementation spec for migration
phase1-data-flow.md | Data flow documentation
data-flow-whitepaper.md | Data flow and data model white paper
observability-plan.md | Monitoring strategy (platform-native vs Datadog)
primers/system-architecture-primer.md | System architecture overview for onboarding
primers/data-model-primer.md | Data model reference
primers/upstash-redis-primer.md | Upstash Redis capabilities
primers/upstash-workflow-primer.md | Upstash Workflow capabilities
primers/upstash-qstash-primer.md | Upstash QStash capabilities